## Sheet1
#SL | Metrics | Formula / Description | Result (%)
1 | Percentage of Test Cases Executed | (Executed TC / Total TC) × 100 | (91/91) ×100 = 100%
2 | Percentage of Test Cases Not Executed | (Not Executed TC / Total TC) × 100 | (0/91) ×100 = 0%
3 | Percentage of Test Cases Passed | (Passed TC / Executed TC) × 100 | (62/91) ×100 = 68.13%
4 | Percentage of Test Cases Failed | (Failed TC / Executed TC) × 100 | (29/91) ×100 = 31.87%
5 | Percentage of Test Cases Blocked | (Blocked TC / Executed TC) × 100 | (0/91) ×100 = 0%
6 | Defect Density | No. of Defects Found / Size of Requirements | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) ×100 | N/A
8 | Defect Leakage | (Defects Found in UAT / Defects Found in Testing) ×100 | N/A
9 | Defect Rejection Ratio | (Rejected Defects / Total Defects Raised) ×100 | N/A
10 | Defect Age | Fixed Date – Reported Date | N/A
11 | Customer Satisfaction | No. of Complaints per Period of Time | N/A
Priority Level | Number of Test Cases | Percentage
High Priority | 82 | (82/91) ×100 = 90.11%
Medium Priority | 5 | (5/91) ×100 = 5.49%
Low Priority | 4 | (4/91) ×100 = 4.40%
Test Metrics Analysis:
All test cases were executed successfully, resulting in 100% execution coverage.
Around 68.13% of the test cases passed successfully.
The failure rate is 31.87%, which indicates several defects still exist in the system.
No test cases were blocked or left unexecuted.
Most of the testing focused on high-priority functionalities (90.11%), ensuring critical system features were validated thoroughly.
The failed test cases should be fixed and retested before deployment to improve system reliability and stability.